|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  | project progress  report#2 | | | | |
| Project Name | Company Rating Website | Project Code | CRW |
| Author | Nguyễn Sơn Lâm | Project Manager | Trần Quốc Hưng |
| Date of Report | 31/07/2016 | Receiver | Supervisor |
| Reporting period | 04/07/2016-31/07/2016 | Bùi Đình Chiến |

# **Progress Description**

|  |  |  |
| --- | --- | --- |
| Items | Information | Note |
| Start-date of project | 09/05/2016 |  |
| Estimated end-date | 27/08/2016 |  |
| Team size | 5 members | Trần Quốc Hưng  Nguyễn Sơn Lâm  Nguyễn Việt Hùng  Nguyễn Nhật Quang  Trần Đăng |
| Total estimated effort | 400 person days | 1 person day = 5 hours |
| Total effort spent | 275 person days | 1 person day = 5 hours |
| Effort spent in this period | 125 person days |  |
| Total effort left | 125 person days |  |

# **Customer Complaints[[1]](#footnote-1)**

## **None**

# **Customer Support[[2]](#footnote-2)**

## **None**

# **Change Management[[3]](#footnote-3)**

## **None**

# **Quality Activities**

## **None**

# **Tasks matches/missed**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Status | Remark | Re-schedule |
| Coding Client Module | HungNV, DangT, HungTQ | 06/06/2016 | Done |  |  |
| Coding Admin Module | HungNV, DangT | 13/06/2016 | Done |  |  |
| Update Screen Design | HungTQ |  | 70% |  |  |
| Create Test Plan | LamNS | 20/07/2016 | Done |  |  |
| Create Integration Test Case | LamNS | 25/07/2016 | Done |  |  |
| Create System Test Case | QuangNN | 25/07/2016 | Done |  |  |
| Domain & Hosting | LamNS |  | 80% |  | 07/08/2016 |
| Run Test Round 1 | QuangNN, LamNS |  | 50% |  |  |
| Progress Report 3 | LamNS | 31/07/2016 | Done |  |  |

# **Tasks planned for next period**

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Planned end date |
| Complete Unit Test | HungNV, DangT, LamNS | 04/08/2016 | 04/08/2016 |
| Run test Rount 1 | LamNS. QuangNN | 04/08/2016 | 04/08/2016 |
| Fix bug Round 1 | HungNV, DangT, HungTQ | N/A | 11/08/2016 |
| Update Test Case | LamNS, QuangNN | N/A | 14/08/2016 |
| Update Test Report | LamNS | N/A | 08/08/2016 |
| Progress report 4 | LamNS | 08/07/2016 | 08/07/2016 |

# **Problems and Suggestions**

# **None**

***Author***

***Nguyễn Sơn Lâm***

1. If no customer complaint is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-1)
2. If no customer request is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-2)
3. If no change request is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-3)