|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  | project progress  report#2 | | | | |
| Project Name | Company Rating Website | Project Code | CRW |
| Author | Nguyễn Sơn Lâm | Project Manager | Trần Quốc Hưng |
| Date of Report | 20/06/2016 | Receiver | Supervisor |
| Reporting period[[1]](#footnote-1) | 09/05/2016-28/05/2016 | Bùi Đình Chiến |

# **Progress Description**

|  |  |  |
| --- | --- | --- |
| Items | Information | Note |
| Start-date of project | 09/05/2016 |  |
| Estimated end-date | 27/08/2016 |  |
| Team size | 5 members | Trần Quốc Hưng  Nguyễn Sơn Lâm  Nguyễn Việt Hùng  Nguyễn Nhật Quang  Trần Đăng |
| Total estimated effort | 400 person days | 1 person day = 5 hours |
| Total effort spent | 150 person days | 1 person day = 5 hours |
| Effort spent in this period | 75 person days |  |
| Total effort left | 250 person days |  |

# **Customer Complaints[[2]](#footnote-2)**

## **None**

# **Customer Support[[3]](#footnote-3)**

## **None**

# **Change Management[[4]](#footnote-4)**

## **None**

# **Quality Activities**

## **None**

# **Tasks matches/missed**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Status | Remark | Re-schedule |
| Create demo | Dev Team | 06/06/2016 | Done |  |  |
| Research development technology | Dev Team | 13/06/2016 | Done |  |  |
| Screen Design | HungTQ | 06/06/2016 | Done |  |  |
| Architecture Design | DangT, HungNV, QuangNN | 20/06/2016 | Done |  |  |
| Database Design | DangT, HungNV, QuangNN | 20/06/2016 | Done |  |  |
| Details Design | DangT, HungNV, QuangNN |  | 80% |  |  |
| Domain & Hosting | LamNS | 30/06/2016 | 50% |  |  |
| Coding Guideline | DangT | 20/06/2016 | Done |  |  |
| Progress Report 2 | LamNS | 20/06/2016 | Done |  |  |

# **Tasks planned for next period**

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Planned end date |
| Domain & Hosting | LamNS | 30/06/2016 | 30/06/2016 |
| Test Plan | LamNS | 04/07/2016 | 04/07/2016 |
| Integration Test | LamNS | 04/07/2016 | 04/07/2016 |
| System Test | LamNS | 09/07/2016 | 09/07/2016 |
| Coding | Dev Team | 09/07/2016 | 18/07/2016 |
| Details Design | DangT, HungNV, QuangNN |  |  |
| Progress report 3 | LamNS | 09/07/2016 | 09/07/2016 |

# **Problems and Suggestions**

|  |  |  |
| --- | --- | --- |
| Task | Description | Solution |
| Hosting at Amazon Web Service | Dorm’s internet blocks port 22, which is necessary to use SSH command at Amazon Web Service | - Use 3G connection (temporary)  - Try to change default SSH port (22) to port 80 (technically not recommended) |

# 

***Author***

***Nguyễn Sơn Lâm***

1. [↑](#footnote-ref-1)
2. If no customer complaint is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-2)
3. If no customer request is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-3)
4. If no change request is received, it is noted as "None", and the table should be deleted [↑](#footnote-ref-4)