## Cover
Quality Management System
CRW_Test Report
CRW
Version : 1.0
Document Control information
Issue Date: | 2016-04-08
Issue Status: | Approved
Author: | Nguyễn Sơn Lâm
Reviewer information | Nguyễn Nhật Quang | Member | Required
Approver information | Trần Quốc Hưng | PM
Document Revision History
Date | Version | Description | Revised by
2016-04-08 | 1 | Create document | Nguyễn Nhật Quang

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 30TC/KLOC | 3 -4 defects/KLOC | 337 | 4 defects/KLOC | 100% | 100% | 0%
Integration Test | 20TC/KLOC | 2 -3 defects/KLOC | 200 | 1 defects/KLOC | 100% | 96% | 4%
System Test | 40TC/KLOC | 4 -6 defects/KLOC | 502 | 5 defects/KLOC | 100% | 96% | 4%
Acceptance Test | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total | 90TC/KLOC | 9-13 defects/KLOC | 1039 | 10 defects/KLOC | 100% | 97% | 3%
Phase | Round 1 |  |  |  | Round 2 |  |  |  | Round 3
| Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A
Unit Test | 337 | 0 | 0 | 0 | 337 | 0 | 0 | 0 | 337 | 0 | 0 | 0
Integration Test | 142 | 42 | 0 | 30 | 180 | 20 | 0 | 0 | 192 | 8 | 0 | 0
System Test | 300 | 90 | 0 | 130 | 450 | 54 | 0 | 2 | 484 | 20 | 0 | 2
Total | 779 | 132 | 0 | 160 | 967 | 74 | 0 | 2 | 1013 | 28 | 0 | 2
Defect report |  | Defect details
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 12 | 100% | 0% | 0%
Medium | 29 | 90% | 0% | 10%
Low | 28 | 100% | 0% | 0%
Total | 50 | 96% | 0% | 4%
Defects category | Open | Closed | Total
Function | 0 | 17 | 17
Message Rules | 0 | 8 | 8
UI | 3 | 41 | 44
Assignee | Open | Closed | Total
LamNS | 0 | 0 | 0
HungTQ | 3 | 35 | 38
QuangNN | 0 | 0 | 0
HungNV | 0 | 25 | 25
DangT | 0 | 6 | 6